## index
<ProjectP> Project Plan
Index
Version: 1.0
Date: 2016/October
Author: Alberto Rodrigues da Silva
ProjectLingo's Project Excel Template (ProjectLingo-Project-Excel-Template)
Copyright
Copyright 2016 INESC-ID, Instituto Superior Técnico, Universidade de Lisboa. All rights reserved. This material is available for academic, research and business purposes, however, You should keep the authors and copyright notice. Any use of this software constitutes full acceptance of all terms of the software's license.
Description
This repository publishes the “ProjectLingo's Project Excel Template” that is a Project template based on the multi-view architecture and inspired on PM standards and frameworks such as ISO 21500, PMI PMBoK, IAPPM, IPMA. This template includes the following files: ProjectLingo-Project-Excel-Template-vX.Y.xlsx: the "PSLingo Project Excel template" that can be customized or directly used in a project basis (please use its most recent version) ProjectLingo-DemoProject-vX.Y.xlsx: an Excel file with a simple (and not complete) application example of this "Project Excel template"; Use its last version as a starting point for your learning and use purpose.
Feedback
Feel free to use it! We would appreciate your feedback,
alberto.silva@tecnico.ulisboa.pt
Licence
ProjectLingo-Project-Excel-Template is released under the EUPL 1.1 licence. http://joinup.ec.europa.eu/software/page/eupl
For further details please consult the LICENCE file.
For further information see:
https://github.com/ProjectLingo

## project
Back to Index
<ProjectP> Project Plan
Project - Main Data
Project Identification
Project # | P_SystemS | Name | Project_SystemS
Type | SystemDesign | Application Domain | Health
Project Progress | Plan
Entities | Name | Sponsor | Proj. Manager
Customer Org | TheCustomerOrg | Mr. Fox | Mrs Eagle
Performing Org | ThePerformingOrg | Ms. Black | Mr. Brown
Other Org | TheOtherOrg | Ms. Friday | ---
Time | Planned | Actual | Variance
Start | 2017-01-02
End | 2018-03-30
Nº Months | 15
Cost | Planned | Actual | Variance
Price | 90000 |  | -90000
Cost | 70000 |  | -70000
Profit | 20000 |  | -20000
Executive Summary | TBD
Purpose: Why? | TBD
Purpose: What? | TBD
Business benefits | TBD
Success Criteria | TBD
Success Factors | TBD

## charter
Back to Index
<ProjectP> Project Plan
Project Charter
Project Name | Project_SystemS | Project # | P_SystemS
Project Sponsor | Ms. Black | Proj.Manager | Mr. Brown
Application Domain | Health | Type | SystemDesign
Dates
Plan Dates: Start | 2017-01-02 | End | 2018-03-30
Executive Summary | TBD
Purpose: Why? | TBD
Purpose: What? | TBD
Business benefits | TBD
Success Criteria | TBD
Success Factors | TBD
Signatures
Sponsor
Signature
Printed name
Date
Project manager
Signature
Printed name
Date

## wbs
Back to Index
<ProjectP> Project Plan
Scope Management :: Work Breakdown Structure
Project
Sub-project, Phase
Workpackage
[5 empty] | Planned Dates |  | Estimated Dates |  | Actual Dates
Id (*) | Name (*) | Type (*) | PartOf | Description | Start | End | Start | End | Start | End | Project Progress
T | Project_SystemS | Project |  | The Project | 2017-01-02 | 2018-03-30 |  |  |  |  | Plan
T_1 | Project Management | Phase | T | Project Management tasks
T_1_1 | Startup | Workpackage | T_1 | Project Management Startup tasks
T_1_2 | Control | Workpackage | T_1 | Project Management Control & Monitor tasks
T_1_3 | Close | Workpackage | T_1 | Project Management Close tasks
M_3 | Project Final Report Approved | Milestone | T_1_3 | Project Final Report Approved |  | 2018-03-22
T_2 | System Definition | Phase | T | System Definition phase
T_2_1 | ... | Workpackage | T_2 | ...
T_2_2 | ... | Workpackage | T_2 | ...
T_3 | System Implementation | Phase | T | System Implementation phase
T_3_1 | ... | Workpackage | T_3 | ...
T_4 | System Deployment | Phase | T | System Deployment tasks
T_4_1 | ... | Workpackage | T_4 | ...
T_4_2 | ... | Workpackage | T_4_1 | ...

## milestones
Back to Index
<ProjectP> Project Plan
Scope Management :: Milestones Table
Id (*) | Name (*) | Type (*) | WorkPackage | Description | Plan | Estimated | Actual | Status
M_1 | Project Plan Approved | Main | T_1_1 | Project Plan Approved | 2017-01-10 |  |  | NotReached
M_3 | Project Final Report Approved | Minor | T_1_3 | Project Final Report Approved | 2018-03-22 |  |  | NotReached
D_3 | System Requirements Specification Approved | Main | T_2_2 | System Requirements Specification Approved |  |  |  | NotReached

## deliverables
Back to Index
<ProjectP> Project Plan
Scope Management :: Deliverables Table
[5 empty] | Planned Dates |  | Estimated Dates |  | Actual Dates
Id (*) | Name (*) | Type (*) | WorkPackage | Description | Submitted | Approved | Submitted | Approved | Submitted | Approved | Status
D_1 | Project Plan | Documentation | T_1_1 | Project Plan Report | 2017-01-07 | 2017-01-10 |  |  |  |  | Approved
D_2 | Project Final Report | Documentation | T_1_3 | Project Final Report | 2018-03-17 | 2018-03-22 |  |  |  |  | NotSubmitted
D_3 | System Requirements Specification | Documentation | T_2_2 | System Requirements Specification Report | [6 empty] | NotSubmitted
D_4 | Status Report | Documentation | T_1_2 | Status Report | [6 empty] | NotSubmitted
D_5 | Progress Report | Documentation | Many | Progress Report | [6 empty] | NotSubmitted
D_6 | System_X | Software.Application | T_4_1 | System_X | [6 empty] | NotSubmitted
Formulas:
Approved = [Planned Dates]+3

## obs
Back to Index
<ProjectP> Project Plan
Organization Management :: Organization Breakdown Structure
Groups of
Individuals
Id (*) | Name (*) | Type (*) | Role (*) | Organization (*) | PartOf | ReportTo | CommunicateWith | Description
Customer Organization
Stk_CG_1 | Steering Committee | Group_Team | Other | Customer |  |  |  | TheProjectOwner
Stk_C_PO | TheProjectOwner | Individual_Person | ProjectOwner | Customer | Stk_CG_1 |  |  | TheProjectOwner
Stk_C_FM1 | TheMarketingDirector | Individual_Person | FunctionalManager | Customer | Stk_CG_1 |  |  | TheMarketingDirector
Stk_C_FM2 | TheOperationDirector | Individual_Person | FunctionalManager | Customer | Stk_CG_1 |  |  | TheOperationDirector
Stk_C_PM | TheCustomerPM | Individual_Person | ProjectManager | Customer |  | Stk_CG_1 | Steering Committee members, TLs, etc | TheCustomerPM
Performing Organization
Stk_P_PM | ThePerformingOrgPM | Individual_Person | ProjectManager | Performing |  | Stk_C_PM |  | ThePerformingOrgPM
Stk_PG_1 | TeamA | Group_Team | Other | Performing |  |  |  | TeamA
Stk_P_TLA | TheTLeaderA | Individual_Person | TeamLeader | Performing | Stk_PG_1 | Stk_P_PM |  | TheTLeaderA
Stk_P_TMA1 | TheMemberA_1 | Individual_Person | TeamMember | Performing | Stk_PG_1 | Stk_P_TLA |  | TheMemberA_1
Stk_P_TMA2 | TheMemberA_2 | Individual_Person | TeamMember | Performing | Stk_PG_1 | Stk_P_TLA |  | TheMemberA_2
Stk_PG_2 | TeamB | Group_Team | Other | Performing |  |  |  | TeamB
Stk_P_TLB | TheScrumMaster | Individual_Person | TeamLeader | Performing | Stk_PG_2 | Stk_P_PM | TheMarketingDirector | TheScrumMaster

## ram
Back to Index
<ProjectP> Project Plan
Organization Management :: Responsability Assignment Matrix
| Stakeholders/Roles |  |  |  |  | Performing Org
|  | TheProjectOwner | TheMarketingDirector | TheOperationDirector | TheCustomerPM | ThePerformingOrgPM | TheTLeaderA | TheScrumMaster
Workpackages |  | Stk_C_PO | Stk_C_FM1 | Stk_C_FM2 | Stk_C_PM | Stk_P_PM | Stk_P_TLA | Stk_P_TLB
T_1 | Project Management
T_1_1 | Startup | D | d | C | C | X | C | C
T_1_2 | Control |  |  |  |  | X
T_1_3 | Close | D |  | d | d | X | C | C
T_2 | System Definition
T_2_1 | ...
T_2_2 | ...
T_3 | System Implementation
T_3_1 | ...
T_4 | System Deployment
T_4_1 | ...
T_4_2 | ...
Legend:
X – executes the work
D – takes the Decision solely or ultimately
d - Takes the decision jointly or partly
P – controls Progress
T – provides Tuition on the job
I – must be Informed
C – must be Consulted
A – available to Advise

## comm.flow
Back to Index
<ProjectP> Project Plan
Communication Management :: Communication Flows
What |  |  |  | Who |  | When |  | How
Id (*) | Deliverable (*) |  | Type (*) | Owner (From) | Audience (To) | Frequency | When | Medium | Format | Description
CF_1 | D_4 | Status Report | Management | Project Manager | Steering Committee | Monthly | Last Wednesday of each month, until 6 PM | ViaEmail | Email | ...
CF_2 | D_5 | Progress Report | Management | Team Leaders | Project Manager | Weekly | Every Thursday, until 6 PM | Other | Collaborative tool | ...

## comm.meet
Back to Index
<ProjectP> Project Plan
Communication Management :: Meetings
Id (*) | Name (*) | Type (*) | Medium | Frequency | Owner | Audience | Deliverable(s) | Format | Description
CM_1 | Kickoff Meeting | Management | Face-to-face | Once | Project Manager | Sponsor, Team Leaders, Team Members (opc), Funcional Managers (opc) | Agenda, Meeting Minutes | Soft copy archived on project SharePoint site and project web site | Introduce the project team and the project. Review project objectives and management approach.
CM_2 | Project Team Meetings | Management | Face-to-face | biweekly | Project Manager | Team Leaders, Team Members | Agenda, Meeting Minutes, Project schedule | Soft copy archived on project SharePoint site and project web site | Review status of the project with the team.
CM_3 | Monthly Project Status Meetings | Management | Face-to-face | Monthly | Project Manager | Steering Committee | Slide updates, Project schedule | Soft copy archived on project SharePoint site and project web site | Report on the status of the project to management.

## issues
Back to Index
<ProjectP> Project Plan
Issue Tracker
# | Issue | Type(*) | Priority | Open Date | Open By | Close Date | Close By | Released Version | Comments
I_1 | print record | Error | High | 2006-07-01 | Bob | 2006-07-01 | Alice |  | done
I_2 | User management and user profile not ... | Error | High | 2006-07-01 | Bob | 2007-07-01 | Alice |  | fixed
I_3 | Search feature... | Change | Medium | 2006-07-01 | Mary | 2019-07-01 | John |  | done, but ...
I_4 | interface XPP: need to add ... | Change | Medium | 2006-07-01 | Mary |  |  |  | ...

## .config
Back to Index
<ProjectP> Project Plan
General Configuration
Project Types
Type: | SystemDevelopment | SystemDesign | SystemDeployment | SystemMaintenance | Training | Research | Other
ApplicationDomain | PublicSector | Education | Health | Telecoms | EnergyAndUtilities | FinanceAndBanks | Other
ProgressState | NotPlan | Plan | OnDesign | OnDevelop | OnTest | OnDeploy | Concluded
System Types
Type: | System | SubSystem | ReusableSystem | Other
Category: | Software | Hardware | Software; Hardware | Other
ScopeType | In | Out
InteractionType | In | Out | In-Out
InteractionCategory | Import | Export | Import-Export | Sync | Interact | Other
Glossary Types
Type: | Stakeholder | Entity | Architectural | Actor | Stakeholder_Actor | Stakeholder_Entity | Stakeholder_Actor_Entity
POS (part-of-speech): | Adjective | Adverb | Noun | Verb
Synset:
Term Relation Type: | Antonym | Hypernym | Synonym
Business_Trainer
Stakeholder Types
Type: | Group_Organization | Group_BusinessUnit | Group_Team | Individual_Person | Individual_ExternalSystem | Other
Category: | Business | Business_Customer | Business_Customer_Sponsor | Business_Customer_Other | Business_User_Direct | Business_User_Indirect | Business_Government | Business_Regulatory | Business_Advisor | Business_System
DependsOn Type | is-part-of
Other Types
Boolean | Yes | No
Scope
TaskType | Project | Sub-Project | Phase | Workpackage | Milestone | Activity | Other
DeliverableType | Documentation | Software.Application | Software.Infrastructure | Hardware | Network.Infrastructure | Other
DeliverableStatus | NotSubmitted | InReview | Approved | Rejected
MilestoneType | Main | Minor | Other
MilestoneStatus | NotReached | Reached
Organization & Stakeholder Types
OrganizationType | Customer | Performing | SubContractor | Other
Type: | Group_Organization | Group_BusinessUnit | Group_Team | Individual_Person | Individual_ExternalSystem | Other
Category: | ProjectOwner | ProjectSponsor | ProjectManager | TeamLeader | TeamMember | FunctionalManager | Other
DependsOn Type | is-part-of
ResponsabilityType | X | P | D | d | C | A | I | T
Communication Types
MeetingType | is-part-of X: Tecnical; is-part-of P: Management; is-part-of D: Steering; is-part-of d: Other
CommunicationMedium | is-part-of X: Face-to-face; is-part-of P: ConferenceCall; is-part-of D: ViaEmail; is-part-of d: Other
CommunicationFrequency | Once | Weekly | biweekly | Monthly | As-Needed